## Summary
Stemacle Feature Status
Canonical workbook | /Users/eric/GitHub/stem-player/docs/stemacle-user-stories-status.xlsx
Last updated | 2026-06-26
Total user stories | 75
Open errors | 0
Current loop | Bulletproofed all contracts: Cloudflare Worker API test suite, 3 separation-server shapes pinned+documented, web↔core DSP parity guards, and decommissioned the dead Electron/Capacitor/SwiftPM-macOS CI/release cluster (CI now honest+green).
Status | Count | Meaning
Retested Pass | 75 | Verified again after fixes
Needs Test | 0 | Inventoried but not yet verified this loop
Fail | 0 | Tested and failed, linked to Errors sheet
Closed Errors | 8 | Documented errors fixed and retested

## User Stories
Story ID | Surface | Area | Feature | User Story | Expected Behavior | Source | Coverage | Status | Test Method | Result | Errors | Fix Status | Retest Result | Priority
WEB-001 | Web | Landing | Release shelf | As a visitor, I can see Stemacle release options without being sent through a marketing funnel. | The landing page shows web app, Mac DMG, Mac ZIP, iOS App Store, GitHub release, and repo links with terse labels and release artwork. | index.html; tests/stem-player.test.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-002 | Web | Legacy Redirect | Legacy stem-player redirect | As a legacy visitor, I am redirected from /stem-player paths to the canonical Stemacle app. | Legacy path preserves tail, query, and hash while sending users to https://stemacle.com/app. | stem-player/index.html; 404.html; scripts/prepare-site.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-003 | Web | Public Pages | Privacy, terms, support | As a user, I can reach privacy, terms, and support pages from public destinations. | Privacy and support pages have real titles/content; support exposes GitHub issue and review links. | privacy/index.html; terms/index.html; support/index.html | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-004 | Web | Boot | Canonical app boot | As a browser user, I can open /app/ without script crashes. | The app boots in a real browser, renders core controls, and produces no uncaught ReferenceError or TypeError. | app/index.html; tests/browser-parity.browser.mjs; tests/stem-player.guards.test.mjs | Browser/static tests | Retested Pass | npm run test:browser; npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-005 | Web | Brand Chrome | Persistent app mark | As a user, I can recognize the app via persistent Stemacle icon chrome. | The app mark and brand tentacle assets render with absolute /assets paths and remain visible. | app/index.html | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Low
WEB-006 | Web | Audio Intake | File chooser | As a user, I can choose a local audio file to split. | The center circle opens a hidden audio file input accepting audio types and common audio extensions; selected files pass to handleFile. | app/index.html | Static + browser | Retested Pass | Browser DOM/manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-007 | Web | Audio Intake | Drag and drop | As a user, I can drop an audio file onto the device. | Drag events highlight the device/center, prevent browser navigation, and dropped files pass to handleFile. | app/index.html | Static + browser | Retested Pass | Browser DOM/manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-008 | Web | Audio Intake | Bundled samples | As a new user, I can try bundled sample tracks. | Three bundled sample buttons render, load same-origin sample MP3s, hide during processing/ready states, and show temporary loading/blocked/failed labels. | app/index.html; samples/*.mp3 | Automated + gated E2E | Retested Pass | npm run test:browser; optional STEMACLE_BROWSER_E2E=1 | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-009 | Web | Native Bridge | Pending native-library track | As a desktop-shell user, I can open a pending library track inside the web app. | openPendingNativeTrack reads a native bridge or IndexedDB/session entry when present, but safely no-ops when browser globals are missing. | app/index.html; tests/stem-player.guards.test.mjs | Automated guard tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-010 | Web | Processing | Processing overlay | As a user waiting for separation, I see progress and can cancel. | Processing overlay shows title/message/progressbar, hides sample rows, and cancel marks the active processing job canceled. | app/index.html | Static + behavioral tests | Retested Pass | npm test; browser manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-011 | Web | Processing | Audio decode timeout | As a user with a problematic file/browser, I am not stuck forever while decoding. | Suspended AudioContext resume and decodeAudioData both time out and recover instead of hanging. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-012 | Web | Processing | Model download timeout/fallback | As a user with a stalled model download, I still get a fallback split path. | Stalled model streams abort/cancel after idle timeout so processing can continue via DSP fallback. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-013 | Web | Separation | Four-stem output | As a user, loaded audio becomes drums, vocals, bass, and melody stems. | The app creates canonical stems in fixed order and maps labels/controls to the correct buffers. | app/index.html; tests/stem-player.guards.test.mjs | Automated guard tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-014 | Web | Tempo | Tempo and downbeat estimation | As a looper, I get plausible BPM and measure grid snapping. | Tempo estimator prefers plausible candidates, preserves precise BPM, and detects a 4/4 downbeat offset when confidence allows. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-015 | Web | Transport | Play/pause/restart/stop | As a listener, I can control playback. | Play waits for AudioContext resume, pause toggles from the same button, restart seeks to zero and plays, stop resets to zero. | app/index.html; tests/stem-player.test.mjs | Automated + browser | Retested Pass | npm test; browser manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-016 | Web | Transport | Timeline seek | As a listener, I can seek through the whole track. | Clicking the timeline seeks by percentage; keyboard arrows/Home/End move accessibly and update aria-valuenow. | app/index.html | Static + browser | Retested Pass | Browser DOM/manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-017 | Web | Visualization | Passive top circle level meter | As a listener, the circle behaves like a display rather than hidden controls. | Quadrants/labels are hidden; a canvas level meter renders live/fallback bass and treble waveform energy. | app/index.html; tests/stem-player.test.mjs | Automated unit/static tests | Retested Pass | npm test; npm run test:browser | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-018 | Web | Visualization | Stem spectrogram lanes | As a remixer, I can see each stem's activity. | Every stem row has a dedicated spectrogram canvas and play cursor, separate from controls. | app/index.html; tests/stem-player.test.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-019 | Web | Visualization | Rolling/expanded spectral window | As a looper, the visible window follows relevant audio. | Normal playback uses a rolling slice; active loops expand the window to include earliest looped audible time and transport with padding. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-020 | Web | Visualization | Spectrogram click seek | As a user, clicking an empty spectrogram lane seeks within the visible window. | Spectrogram click maps client X to the current visible time span and calls seek without creating a loop. | app/index.html; tests/stem-player.test.mjs | Automated unit + browser | Retested Pass | npm test; browser manual | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-021 | Web | Visualization | Grid markers | As a looper, I can see quarter/half/measure timing markers. | Grid markers derive from BPM/measure offset and label 1/4, 1/2, and 1 positions. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-022 | Web | Mixing | Per-stem volume | As a remixer, I can adjust each stem level without resizing the UI. | Each stem slider writes 0..1 volume, preserves defaults at 0.8, and applies gain immediately. | app/index.html; tests/stem-player.test.mjs | Automated unit/static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-023 | Web | Mixing | Per-stem mute | As a remixer, I can mute individual stems. | Mute toggles visual/aria state and gain without changing stored volume. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-024 | Web | Mixing | Headphones solo isolation | As a remixer, I can isolate one stem in headphones mode. | Only the selected stem is audible, mute/volume state is not mutated, and turning it off restores mix state. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-025 | Web | Mixing | Global mute toggle | As a listener, I can mute or unmute all stems with one persistent control. | One button toggles all mute states, updates aria label/pressed text, clears headphones, and preserves volume values. | app/index.html; tests/stem-player.test.mjs | Automated unit/static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-026 | Web | Loops | Per-stem loops | As a remixer, I can loop a single stem by 1/4, 1/2, 1, or 2 measures. | Loop buttons snap to the selected subdivision and reschedule only the selected stem when playing. | app/index.html; tests/stem-player.test.mjs | Automated unit + gated browser | Retested Pass | npm test; optional STEMACLE_BROWSER_E2E=1 | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-027 | Web | Loops | All-row linked loop | As a remixer, I can apply one loop window to all stems. | All row sets/clears the same quantized loop across every stem and updates all stem loop UI. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-028 | Web | Loops | Mix/Solo loop monitoring | As a looper, I can audition loops in context or solo. | Mix mode keeps looped stems in full mix; Solo mode cues looped stems via headphones without mutating mute state. | app/index.html; tests/stem-player.test.mjs; tests/browser-parity.browser.mjs | Automated + gated browser | Retested Pass | npm test; npm run test:browser | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-029 | Web | Loops | Loop-past-end rejection | As a looper near the end of a track, I get a clear rejection rather than stale state. | Loops that exceed duration alert the user, clear stale loop UI/state, and do not shrink into a shorter loop. | app/index.html; tests/stem-player.test.mjs | Automated unit tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-030 | Web | Loops | New-load loop reset | As a user loading a new song, old loops do not leak into the new track. | handleFile/finish load clears loop state, loop UI, and loop audition state before ready. | app/index.html; PRODUCT.md | Static + behavioral | Retested Pass | npm test; code review | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | High
WEB-031 | Web | Responsive | Mobile controls and sample labels | As a phone user, controls fit without text overlap. | Transport/buttons have fixed hit areas; sample titles wrap inside responsive buttons; stem rows reflow on small screens. | app/index.html; tests/stem-player.test.mjs | Automated static + browser screenshot | Retested Pass | npm test; browser screenshot | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. |  | Not Applicable | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Medium
WEB-032 | Web | Stem Shuffle Web | Compatibility handoff | As a web visitor to Stem Shuffle, I am routed to current surfaces. | Stem Shuffle web page explains the move and links to Stem Splitter and native app releases; legacy implementation files are gone. | apps/stem-shuffle/index.html; tests/stem-shuffle.test.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | ERR-002 | Fixed | Retested Pass: npm test passed 75/75; browser parity passed 10/10 with STEMACLE_BROWSER_E2E=1. | Low
APPLE-001 | Apple | Architecture | Native SwiftUI app | As an Apple user, I get a native SwiftUI app over StemacleKit, not a webview shell. | Project defines macOS and iOS targets using StemacleKit/XCFramework and app imports SwiftUI without WKWebView. | native/apple/project.yml; native/apple/Stemacle/*.swift; tests/native-apps.test.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-002 | Apple | Navigation | Tabbed shell | As an Apple user, I can move between Library, Splitter, Settings, and intended Shuffle/Mixer surfaces. | TabView exposes reachable tabs matching implemented surfaces, with Import reachable from key tabs. | native/apple/Stemacle/StemacleApp.swift; native/apple/Stemacle/Mixer.swift | Code review + compile | Retested Pass | npm test; xcodebuild if available | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | ERR-001 | Fixed | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-003 | Apple | Import | Persistent import | As an Apple user, I can change songs without exiting the player. | Library Add and Splitter plus button open fileImporter for audio and route successful selection to Splitter load. | native/apple/Stemacle/StemacleApp.swift | Code review + UI test | Retested Pass | npm test; xcodebuild/UI | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-004 | Apple | Demo | Try a bundled sample | As a new Apple user, I can load a bundled demo. | Device circle shows try a sample when idle and loads Resources/demo.wav. | native/apple/Stemacle/StemacleApp.swift; native/apple/Stemacle/Resources/demo.wav | Code review + compile | Retested Pass | npm test | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | Medium
APPLE-005 | Apple | Separation | On-device DSP fallback | As an Apple user, I can split offline when no server is configured or reachable. | loadFile decodes stereo 44.1k, tries configured server only when selected, then falls back to Stemacle.separate on a detached task. | native/apple/Stemacle/StemPlayerViewModel.swift | Code review + unit compile | Retested Pass | npm test; xcodebuild if available | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-006 | Apple | Separation | Server model selection | As an Apple user, I can choose on-device, htdemucs, or htdemucs_ft separation. | Settings persists stemacle.model; server submissions include chosen multipart model and unsupported server values fall back. | native/apple/Stemacle/StemacleApp.swift; StemServerClient.swift; server/app.py | Code review + tests | Retested Pass | npm test; server test/manual | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-007 | Apple | Progress | Background split progress | As an Apple user, I can see splitting progress. | Server jobs update splitProgress/status and render an amber progress ring while processing. | native/apple/Stemacle/StemPlayerViewModel.swift; StemacleApp.swift | Code review + UI | Retested Pass | Manual/UI | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | Medium
APPLE-008 | Apple | Library | Project cache | As an Apple user, split songs are saved for instant reopen. | Fresh split writes project metadata plus four stem WAVs under Application Support and updates projects.json. | native/apple/Stemacle/Library.swift; StemPlayerViewModel.swift | Code review + tests | Retested Pass | npm test; xcodebuild if available | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-009 | Apple | Library | Library empty and project rows | As an Apple user, I can see empty guidance and then reopen cached songs. | Empty library shows add guidance; project rows show title, BPM, duration, quality and open into Splitter. | native/apple/Stemacle/StemacleApp.swift; Library.swift | Code review + UI | Retested Pass | Manual/UI | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-010 | Apple | Transport | Native transport | As an Apple user, I can play, pause, stop, restart, and seek. | Transport buttons are disabled until ready; backward seeks to zero; play toggles; stop resets position. | native/apple/Stemacle/StemacleApp.swift; StemAudioEngine.swift | Code review + compile | Retested Pass | npm test; xcodebuild if available | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-011 | Apple | Mixing | Per-stem controls | As an Apple user, I can volume, mute, and solo stems. | Each stem row exposes slider, speaker mute, headphones solo, and applies mixing without losing volume state. | native/apple/Stemacle/StemacleApp.swift; StemAudioEngine.swift | Code review + compile | Retested Pass | npm test; xcodebuild if available | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-012 | Apple | Loops | Native per-stem and all loops | As an Apple user, I can apply snapped loops per stem or all stems. | Loop buttons set/clear 1/4, 1/2, 1, 2 bar windows, reject past-end loops, and reset on new loads. | native/apple/Stemacle/StemPlayerViewModel.swift; StemAudioEngine.swift | Code review + core tests | Retested Pass | npm test; npm run core:test | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | High
APPLE-013 | Apple | Visualization | Spectrogram lanes and visualizer | As an Apple user, I can see master/stem spectrograms, grid markers, play cursor, and radial spectrum. | Loaded stems compute spectrograms; lanes tap-seek; player header renders spinning disc and radial spectrum. | native/apple/Stemacle/StemacleApp.swift; VisualizerViews.swift | Code review + UI | Retested Pass | Manual/UI | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | Medium
APPLE-014 | Apple | Settings | Settings links and server URL | As an Apple user, I can configure the separation server and reach policy/support links. | Settings contains model picker, server URL text field saved to UserDefaults, and Privacy/Terms/Support links. | native/apple/Stemacle/StemacleApp.swift | Code review + UI | Retested Pass | Manual/UI | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. |  | Not Applicable | Retested Pass: npm test passed 75/75; macOS and iOS simulator xcodebuild passed. | Medium
APPLE-015 | Apple | Mixer | Two-song stem routing | As a Stem Shuffle user, I can pick two cached songs and route each output stem from source A or B. | MixerView requires at least two projects, lets user pick Source A/B, route stems with segmented controls, and play/stop mixed buffers. | native/apple/Stemacle/Mixer.swift | Automated unit tests + compile | Retested Pass | swift test (StemRoutingTests); npm test; xcodebuild | Retested Pass: routing logic extracted to StemRouting and covered by 9 unit tests (APPLE-018); npm test 96/96; both Apple builds passed. | ERR-001; ERR-004 | Fixed | Retested Pass: 9 StemRouting unit tests; npm test 96/96; both Apple builds passed. | High
DESK-001 | Desktop | Architecture | Slint desktop shell | As a Windows/Linux user, I get a native Slint shell over the shared Rust core. | Desktop Cargo uses slint and stemacle-dsp, not Electron; UI file exists and player logic is Rust. | native/desktop/Cargo.toml; native/desktop/ui/stemacle.slint; tests/native-apps.test.mjs | Automated static tests | Retested Pass | npm test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-002 | Desktop | Import | Open WAV | As a desktop user, I can open a WAV file. | Open WAV button/file dialog accepts WAV, runs load_stems on a worker thread, and updates status/ready when complete. | native/desktop/src/main.rs; player.rs; ui/stemacle.slint | Rust tests + code review | Retested Pass | npm run desktop:test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-003 | Desktop | Separation | High-quality then DSP fallback | As a desktop user, I get htdemucs when configured and DSP fallback otherwise. | DemucsConfig checks env availability; load_stems returns high_quality true on demucs success or deterministic DSP split on failure/unavailable. | native/desktop/src/player.rs; demucs.rs | Rust tests + optional ignored E2E | Retested Pass | npm run desktop:test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-004 | Desktop | Transport | Play/pause/stop | As a desktop user, I can play, pause, and stop loaded stems. | Buttons are enabled only when ready; AudioOutput toggles play and stop updates UI playing state. | native/desktop/src/main.rs; playback.rs | Rust tests + manual | Retested Pass | npm run desktop:test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-005 | Desktop | Mixing | Volume/mute/solo | As a desktop user, I can mix stems. | Sliders update per-stem volume; mute and H solo update effective gains with solo overriding mute while preserving volumes. | native/desktop/src/main.rs; player.rs; ui/stemacle.slint | Rust tests | Retested Pass | npm run desktop:test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-006 | Desktop | Export | Export four stems | As a desktop user, I can export separated stems. | Export stems button prompts for a folder and writes drums, vocals, bass, and melody WAV files. | native/desktop/src/main.rs; player.rs | Rust tests | Retested Pass | npm run desktop:test | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | High
DESK-007 | Desktop | Format Support | WAV-only intake | As a desktop user, I get clear behavior for unsupported files. | Desktop dialog only advertises Audio (WAV); broader MP3/FLAC support is not shipped. | native/desktop/src/main.rs; docs/FEATURE_MATRIX.md | Code review | Retested Pass | Code review | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. |  | Not Applicable | Retested Pass: npm run desktop:test passed 6/7 with 1 intentional ignored Demucs E2E; native guard tests passed. | Medium
CORE-001 | Core | DSP | Shared Rust DSP core | As any native user, I get consistent stem DSP across surfaces. | Core workspace includes FFT/STFT/HPSS/tempo/loop modules and golden/reconstruction tests pass. | native/core; tests/native-core.test.mjs | Automated Rust tests | Retested Pass | npm run core:test; npm test | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. |  | Not Applicable | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. | High
CORE-002 | Core | FFI | C ABI surface | As an Apple app, StemacleKit can call the shared core safely. | Header and Rust FFI expose separate, free, measure length, snap loop, loop range, and audible stem time functions. | native/core/stemacle-ffi | Automated static tests | Retested Pass | npm test | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. |  | Not Applicable | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. | High
CORE-003 | Core | Loop Contract | Loop timing parity | As a user on any surface, loops snap and wrap consistently. | Rust core loop range/snap/audible-time behavior matches documented loop contract and browser expectations. | native/core/stemacle-dsp/src/loops.rs; specs/LoopTiming.tla | Rust/TLA/static tests | Retested Pass | npm run core:test; npm test | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. |  | Not Applicable | Retested Pass: npm run core:test passed 31 Rust tests; npm test guard coverage passed. | High
SERVER-001 | Server | Health | Health endpoint | As a client, I can check the separation server is up. | GET /healthz returns ok true and the default model name. | server/app.py | Automated guard tests (Node) + optional HTTP | Retested Pass | node --test tests/server-queue.test.mjs | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. |  | Not Applicable | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. | Medium
SERVER-002 | Server | Queue | Submit separation job | As a thin client, I can upload audio for background separation. | POST /separate accepts multipart file and model, stores input, starts background job, returns job_id/status/model. | server/app.py; StemServerClient.swift | Automated guard tests (Node) + optional HTTP | Retested Pass | node --test tests/server-queue.test.mjs | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. |  | Not Applicable | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. | High
SERVER-003 | Server | Model Selection | Allowed server models | As a client, invalid model names cannot break server jobs. | Server accepts htdemucs, htdemucs_ft, mdx_extra and falls back to htdemucs for unknown model values. | server/app.py | Automated guard tests (Node) + optional HTTP | Retested Pass | node --test tests/server-queue.test.mjs | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. |  | Not Applicable | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. | High
SERVER-004 | Server | Progress | Polling job status | As a client, I can poll job progress and errors. | GET /jobs/{id} reports processing/done/error, stems, error, and 0-100 progress. | server/app.py; StemServerClient.swift | Automated guard tests (Node) + optional HTTP | Retested Pass | node --test tests/server-queue.test.mjs | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. |  | Not Applicable | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. | High
SERVER-005 | Server | Download | Download stem WAV | As a client, I can download each completed stem. | GET /jobs/{id}/{stem} returns audio/wav for valid completed stems, 404 when not ready/missing, and 400 for invalid stem names. | server/app.py; StemServerClient.swift | Automated guard tests (Node) + optional HTTP | Retested Pass | node --test tests/server-queue.test.mjs | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. |  | Not Applicable | Retested Pass: 7 Node contract guards over server/app.py + stemacle_sep.py passed (verified non-vacuous). Server retained for a future opt-in (e.g. Cloudflare); not wired into the app. | High
APPSTORE-001 | App Store | Screenshots | Screenshot layout page | As a release maintainer, I can verify App Store screenshot layouts locally. | The screenshot page renders six iPhone slides and six iPad slides with no horizontal overflow at required viewport sizes. | appstore-screenshots/screenshots-v3.html; tests/test_appstore_layout.mjs | Automated browser layout tests | Retested Pass | npm run appstore:verify | Retested Pass: appstore layout verify and both screenshot export scripts passed. | ERR-003 | Fixed | Retested Pass: appstore layout verify and both screenshot export scripts passed. | High
APPSTORE-002 | App Store | Screenshots | Screenshot export scripts | As a release maintainer, I can export iPhone and iPad screenshot PNGs from the canonical screenshot page. | Package scripts export App Store-sized iPhone and iPad PNGs from screenshots-v3.html without needing manual browser capture. | appstore-screenshots/export.js; appstore-screenshots/export-ipad.js; package.json | Automated export smoke | Retested Pass | npm run appstore:export-iphone; npm run appstore:export-ipad | Retested Pass: appstore layout verify and both screenshot export scripts passed. | ERR-003 | Fixed | Retested Pass: appstore layout verify and both screenshot export scripts passed. | High
APPLE-016 | Apple | Separation | macOS local htdemucs subprocess | As a macOS user, when a local Demucs runtime is present my splits use real htdemucs quality (beating the web app) with no audio upload. | SubprocessDemucsConfig.fromEnv resolves python/script/model from STEMACLE_DEMUCS_* env vars; available() gates use; separate() shells out to models/separate.py and reads four mono stem WAVs; loadFile uses it on macOS then falls back to on-device DSP. | native/apple/Stemacle/StemPlayerViewModel.swift; native/apple/StemacleKit/Sources/StemacleKit/SubprocessDemucs.swift | Automated unit tests | Retested Pass | swift test (StemacleKit); xcodebuild macOS | Retested Pass: 6 SubprocessDemucs unit tests; macOS and iOS builds passed. | None | Not Applicable | Retested Pass: 6 SubprocessDemucs unit tests; macOS and iOS builds passed. | High
APPLE-017 | Apple | Privacy | On-device-only separation posture | As an iOS user, my audio is never uploaded; separation runs entirely on-device, matching the App Store privacy promise. | loadFile has no network/server tier on iOS; only macOS adds a LOCAL subprocess tier; the Settings copy "your music stays on this device" holds; guard tests forbid StemServerClient/awaitStems wiring in the ViewModel. | native/apple/Stemacle/StemPlayerViewModel.swift; tests/native-apps.test.mjs | Automated guard tests | Retested Pass | node --test tests/native-apps.test.mjs; xcodebuild | Retested Pass: native guards 16/16; both Apple builds passed. | ERR-006 | Fixed | Retested Pass: native guards 16/16; both Apple builds passed. | High
APPLE-018 | Apple | Mixer | Stem routing logic (StemRouting) | As a Stem Shuffle user, each output stem independently routes to song A or B, and playback needs both songs. | StemRouting defaults every stem to A; toggle flips known stems (unknown = no-op); source(for:a:b:) resolves per stem; canPlay requires both sources. MixerViewModel delegates routing to it. | native/apple/StemacleKit/Sources/StemacleKit/StemRouting.swift; native/apple/Stemacle/Mixer.swift | Automated unit tests | Retested Pass | swift test (StemRoutingTests) | Retested Pass: 9 StemRouting unit tests; both Apple builds passed. | None | Not Applicable | Retested Pass: 9 StemRouting unit tests; both Apple builds passed. | Medium
APPLE-019 | Apple | Audio I/O | WAV codec round-trip + robustness | As the app caching and exchanging stems, 16-bit WAV encode/decode is faithful and robust to bad input. | encodeWav writes a valid header-only WAV for empty input and clamps out-of-range samples; decodeWavMono returns [] for empty/corrupt data and averages stereo channels to mono. | native/apple/StemacleKit/Sources/StemacleKit/StemServerClient.swift | Automated unit tests | Retested Pass | swift test (StemacleKitTests WAV cases) | Retested Pass: 6 WAV codec unit tests passed. | None | Not Applicable | Retested Pass: 6 WAV codec unit tests passed. | Low
APPLE-020 | Apple | UI/UX | Tap targets match visual bounds | As a user, tapping anywhere on a button or list row activates it — not only the text or icon. | SettingsRow and SettingsLinkRow declare .contentShape(Rectangle()) so the Spacer gap is tappable; the Library Add, transport, mute/solo toggle, and change-song (+) buttons reserve a 44pt frame AND a contentShape so the padding around the glyph is live (no dead corners). | native/apple/Stemacle/StemacleApp.swift; tests/native-uiux.test.mjs | Automated guard tests | Retested Pass | node --test tests/native-uiux.test.mjs; xcodebuild | Retested Pass: 6 hit-target guards were RED (real bugs), fixed to green; native-uiux 9/9; both Apple builds passed. | ERR-007 | Fixed | Retested Pass: native-uiux 9/9; npm test 105/105; both Apple builds passed. | Medium
APPLE-021 | Apple | UI/UX | No overlapping chrome | As a user, a long song title never grows under the adjacent button, and Mixer route controls never overlap. | The splitter title is single-line with .minimumScaleFactor(0.75) + .layoutPriority(1) and a Spacer before the + button; Mixer route rows pin the stem name (80pt) and A/B picker (120pt) into fixed lanes separated by a Spacer. | native/apple/Stemacle/StemacleApp.swift; native/apple/Stemacle/Mixer.swift; tests/native-uiux.test.mjs | Automated guard tests | Retested Pass | node --test tests/native-uiux.test.mjs | Retested Pass: overlap guards 3/3 green; both Apple builds passed. | None | Not Applicable | Retested Pass: overlap guards green; both Apple builds passed. | Low
CTRL-001 | Cloudflare | Separation API | Edge Worker HTTP contract | As a future hosted-Demucs client, the edge Worker behaves predictably and never lies about having a GPU/Demucs backend it lacks. | GET /+/healthz healthy; /capabilities discloses demucsOnCloudflareEdge:false + currentBackend:cloudflare_queue_no_gpu_consumer; /quote bounded+clamped; /separate 503-without-bindings, 415-non-JSON, 202-with-bindings (job_id+queue.send+R2.put); /jobs/:uuid 404-unknown, malformed→not_found; OPTIONS 204 CORS. | cloudflare/stemacle-api-worker.js; tests/cloudflare-api.test.mjs | Automated behavioral tests | Retested Pass | node --test tests/cloudflare-api.test.mjs | Retested Pass: 14 behavioral tests (verified non-vacuous); live deployment matches. | None | Not Applicable | Retested Pass: 14 behavioral tests against the worker handler. | High
CTRL-002 | CI | Pipelines | Honest, green CI workflows | As a contributor, CI validates the surfaces that actually exist and does not reference deleted ones. | pages.yml verifies real site+native files (no native/electron, native/index.html, native/ios, capacitor) and drops the broken native:prepare; release.yml runs the test gate on tags without the dead macOS-DMG build. Locked by stem-player.test.mjs honest-contract guards. | .github/workflows/pages.yml; .github/workflows/release.yml; tests/stem-player.test.mjs | Automated guard tests | Retested Pass | node --test tests/stem-player.test.mjs | Retested Pass: CI no longer references deleted surfaces; npm test 142/142. | ERR-008 | Fixed | Retested Pass: honest-CI guards green; npm test 142/142. | High
CTRL-003 | Repo | Cleanup | Dead macOS/Electron/Capacitor release cluster removed | As a new agent, package.json + scripts reflect reality so I am not misled into a dead toolchain. | Removed electron-builder build block, macos:*/native:prepare scripts, scripts/{prepare-native,package-macos}.mjs; package.json scripts carry no electron/capacitor/native-macos references; the lying green macOS-DMG release test was replaced with an honest decommission guard. | package.json; scripts/; tests/stem-player.test.mjs | Automated guard tests | Retested Pass | node --test tests/stem-player.test.mjs | Retested Pass: honest release/package contract guard green. | ERR-008 | Fixed | Retested Pass: honest release/package contract guard green. | Medium
CTRL-004 | Cross-surface | Separation contracts | Three server shapes pinned + documented | As an integrator, the FastAPI server, Swift client, and Cloudflare worker contracts are explicit so I never confuse them. | docs/SEPARATION_CONTRACTS.md documents all three; a guard pins that the Swift client speaks the FastAPI contract (routes, fields, multipart, stems) and that the Cloudflare worker is deliberately distinct (JSON+R2, no per-stem WAV route). | docs/SEPARATION_CONTRACTS.md; tests/separation-contracts.test.mjs | Automated cross-contract tests | Retested Pass | node --test tests/separation-contracts.test.mjs | Retested Pass: 6 cross-contract guards green. | None | Not Applicable | Retested Pass: 6 cross-contract guards green. | High
CTRL-005 | Cross-surface | DSP parity | Web↔Rust core parity for soft crossover + NaN guard | As a maintainer, the bass/melody crossover and BPM NaN guard cannot drift between the web gold master and the Rust core. | Source-parity guards assert web app/index.html and native/core share the 220/380 Hz band, the 0.5+0.5cos(PI t) crossfade, the is-finite BPM fallback to 120, and (60/bpm)*BEATS_PER_MEASURE — the two pieces not covered by golden vectors. | app/index.html; native/core/stemacle-dsp/src/{hpss,loops,tempo}.rs; tests/dsp-parity.test.mjs | Automated parity tests | Retested Pass | node --test tests/dsp-parity.test.mjs | Retested Pass: 5 parity guards (verified non-vacuous). | None | Not Applicable | Retested Pass: 5 parity guards green. | Medium

## Errors
Error ID | Story IDs | Surface | Type | Title | Observed | Priority | Status | Root Cause | Fix | Retest
ERR-001 | APPLE-002; APPLE-015 | Apple | Logistical/UX | Shuffle/Mixer was implemented but unreachable | Tab enum included shuffle and MixerView existed, but AppRootView TabView did not include a Shuffle/Mixer tab item. | High | Closed | Navigation wiring stopped before mounting the implemented MixerView surface. | Mounted MixerView in TabView, added mixer StateObject, Shuffle tab item/tag, and native static coverage. | Retested Pass: native static tests, macOS build, and iOS simulator build passed.
ERR-002 | WEB-032 | Web | Logistical/UX | Stem Shuffle handoff label pointed at a removed native web shell | The compatibility page linked to / with the label "Open desktop shell" even though native/index.html is gone and / is the release shelf. | Low | Closed | Legacy copy and stale browser test still assumed a native web shell. | Changed the handoff label to "Get native apps" and replaced the stale browser assertion with release-shelf handoff coverage. | Retested Pass: stem-shuffle static tests and gated browser parity passed.
ERR-003 | APPSTORE-001; APPSTORE-002 | App Store | Logistical | App Store verification scripts referenced a missing screenshot page/exporters | npm run appstore:verify failed because appstore-screenshots/screenshots-v3.html did not exist; package export scripts also pointed at absent files. | High | Closed | Package scripts and tests existed before their screenshot source artifact was checked in. | Added screenshots-v3.html plus iPhone and iPad Puppeteer exporters. | Retested Pass: appstore verify and both export scripts passed.
ERR-004 | APPLE-015 | Apple | Compile | Mixer helper name shadowed the stems collection | xcodebuild failed in Mixer.swift because a local helper named stems shadowed the stems array used in for stem in stems. | High | Closed | A nested helper function reused the same identifier as the canonical stem collection. | Renamed the helper to cachedStems(for:) and regenerated the Xcode project so Mixer.swift is compiled. | Retested Pass: macOS and iOS simulator builds passed.
ERR-005 | APPLE-016; APPLE-019 | Apple | Logistical | Native source-pattern guards pointed at pre-refactor file layout | After moving StemServerClient + the WAV codec into StemacleKit and adding Demucs tiers, 4 guards in tests/native-apps.test.mjs failed: one read the deleted app-target StemServerClient.swift (ENOENT), one assumed a single-line separation-queue call, and two forbade server wiring in the ViewModel. | Medium | Closed | Guards encoded old file locations and call formatting; the refactor relocated the WAV codec to StemacleKit and line-wrapped the on-device call. | Repointed the WAV guard to StemacleKit and made the queue guard whitespace-tolerant. The two server-wiring guards were satisfied by ERR-006 (removing the upload path), not by weakening them. | Retested Pass: native guards 16/16; npm test 96/96.
ERR-006 | APPLE-017 | Apple | UX/Privacy | iOS gained an audio-upload separation path against the no-upload posture | A new tier in loadFile uploaded audio to StemServerClient.configured() whenever stemacle.serverURL was set, contradicting the shipped Settings promise "Your music stays on this device... no uploads" with no opt-in UI to configure it. | High | Closed | Pursuing htdemucs quality on iOS reintroduced the server queue, but real htdemucs cannot run on-device (documented dead-end), so the only server route conflicts with the App Store privacy positioning. | Per product decision (on-device only; revisit a hosted opt-in like Cloudflare later) removed the server tier from the Apple ViewModel. iOS is on-device DSP only; macOS keeps a LOCAL htdemucs subprocess (no upload). StemServerClient + server/app.py are retained and unit/contract-tested for a future explicit opt-in. | Retested Pass: native guards 16/16; both Apple builds passed; Settings copy is accurate again.
ERR-007 | APPLE-020 | Apple | UX | Button and row tap areas were smaller than their visual bounds | SettingsRow and SettingsLinkRow had a transparent Spacer gap with no contentShape, so taps between the title and the trailing chevron/arrow were dead — you had to hit the text. The Library Add, transport, mute/solo, and change-song icon buttons set a 44pt frame around a ~14-20pt glyph but no contentShape, leaving dead corners. | Medium | Closed | SwiftUI .buttonStyle(.plain) hit-tests only drawn content; a Spacer gap or the empty padding inside a .frame is transparent and not hittable without an explicit .contentShape. | Added .contentShape(Rectangle()) to the settings rows and the transport/change-song icon buttons, .contentShape(Circle()) to the round mute/solo toggle, and a 44pt min frame + contentShape to the Library Add label. | Retested Pass: node --test tests/native-uiux.test.mjs 9/9 (6 previously RED); both Apple builds passed.
ERR-008 | CTRL-002; CTRL-003 | CI | Logistical | CI workflows + package.json referenced surfaces deleted in the native rewrite (CI was RED) | pages.yml asserted 5 deleted files exist (native/index.html, native/electron/main.cjs, native/ios/*, capacitor.config.json) and ran a broken native:prepare (copies the gone native/index.html); release.yml built a macOS DMG from the gone native/macos via electron-builder; a green test in stem-player.test.mjs locked the dead pipeline. | High | Closed | The native rewrite deleted native/electron, native/ios (Capacitor), native/macos (SwiftPM) and the native-bundle shell, but the CI/scripts/tests/package.json referencing them were never updated. | Decommissioned the cluster: cleaned package.json (no build block/main/electron+capacitor deps/dead scripts), deleted scripts/{prepare-native,package-macos,serve-native,desktop-dispatch}.mjs, made pages.yml/release.yml honest, and replaced the lying macOS-DMG test with honest decommission guards. Removed dead test helpers that read gone files. | Retested Pass: npm test 142/142; both Apple targets BUILD SUCCEEDED.

## Test Runs
Run ID | Date | Scope | Command / Method | Status | Notes | Log / Evidence
RUN-001 | 2026-06-25 | Initial code inventory | Code/docs/tests review | Completed | 64 user stories inventoried from current workspace code.
RUN-002 | 2026-06-25 | Web/static/native guard tests | npm test | Pass | 75/75 tests passed after fixes.
RUN-003 | 2026-06-25 | Browser parity and gated user journeys | npm run test:browser; STEMACLE_BROWSER_E2E=1 npm run test:browser | Pass | Normal run passed 7/10 with three gated E2E tests skipped; gated run passed 10/10 including sample splitter-ready, Solo toggle, and loop button journeys.
RUN-004 | 2026-06-25 | Rust core and FFI | npm run core:test | Pass | 31 Rust tests passed across core, golden, and FFI crates.
RUN-005 | 2026-06-25 | Desktop Slint/Rust | npm run desktop:test | Pass | 6 tests passed; 1 high-quality Demucs E2E remains ignored by design. Rust emitted an existing unused-field warning for Shared.sample_rate.
RUN-006 | 2026-06-25 | Apple native builds | xcodebuild -project native/apple/Stemacle.xcodeproj -scheme StemacleMac -configuration Debug -destination 'platform=macOS' build; xcodebuild -project native/apple/Stemacle.xcodeproj -scheme StemacleiOS -configuration Debug -destination 'generic/platform=iOS Simulator' build | Pass | Both macOS and generic iOS simulator builds passed after mounting Mixer/Shuffle and regenerating the project. Existing Swift 6 concurrency warning remains in StemPlayerViewModel.swift.
RUN-007 | 2026-06-25 | App Store screenshot verification/export | npm run appstore:verify; npm run appstore:export-iphone; npm run appstore:export-ipad | Pass | Layout verification passed 2/2 and re-ran npm test 75/75; both export scripts generated screenshots successfully.
RUN-008 | 2026-06-25 | Separation queue server smoke | models/.venv-models/bin/python direct FastAPI endpoint smoke | Pass | Stubbed heavy Demucs module, then exercised healthz, separate model fallback, background completion, job status, stem download, missing-job 404, and invalid-stem 400.
RUN-009 | 2026-06-25 | StemacleKit Swift unit tests | swift test (native/apple/StemacleKit) | Pass | 38 tests: 15 server-client/WAV-codec, 5 subprocess-config, 9 StemRouting, plus core/loop wrappers. All passed. | None
RUN-010 | 2026-06-25 | Rust core extended edge cases | cargo test (native/core/stemacle-dsp) | Pass | 40 tests (36 lib incl. silent-input, sub-FFT-size, exact vocal-mask boundaries, centered voice-range routing; 4 golden parity). All passed. | None
RUN-011 | 2026-06-25 | Server contract guards (Node) | node --test tests/server-queue.test.mjs | Pass | 7 source-contract guards over server/app.py + stemacle_sep.py (health, submit, model allowlist, job status, progress bounds, stem download, stem order/mapping). Verified non-vacuous by a deliberate-break check. | None
RUN-012 | 2026-06-25 | Full Node suite + Apple builds after on-device-only refactor | npm test; xcodebuild macOS + iOS | Pass | npm test 96/96 (incl. new server guards and repaired native guards); both Apple targets BUILD SUCCEEDED. | None
RUN-013 | 2026-06-25 | UIUX hit-target + overlap guards (Apple) | node --test tests/native-uiux.test.mjs | Pass | 9 guards: settings row/link-row contentShape, Library Add + transport + mute/solo toggle + change-song hit targets, title and Mixer overlap. 6 were RED first (real dead-tap-area bugs), fixed to green. | None
RUN-014 | 2026-06-25 | Full Node suite after UIUX fixes | npm test; xcodebuild macOS + iOS | Pass | npm test 105/105 (incl. 9 new UIUX guards); both Apple targets BUILD SUCCEEDED. | None
RUN-015 | 2026-06-26 | Contract hardening: Cloudflare worker + cross-contract + DSP parity | node --test tests/{cloudflare-api,separation-contracts,dsp-parity}.test.mjs | Pass | 14 worker + 6 cross-contract + 5 DSP-parity guards; non-vacuous checks done. Pins the Cloudflare API, the 3 server shapes, and web↔core DSP. | None
RUN-016 | 2026-06-26 | CI/release decommission + honest guards + full suite | npm test; cargo test core; xcodebuild macOS+iOS | Pass | npm test 142/142; Rust core 36 lib + 4 golden + 3 ffi; StemacleKit swift 38; both Apple targets BUILD SUCCEEDED. CI no longer references deleted surfaces. | None